Conference 2017 Report

Name: Max Stenstrom

Position: 2017 Conference Convenor

E-mail: conference2017@alsa.net.au

# What has happened so far...

* Team
	+ Publicised organising committee positions
	+ Received and assessed over 100 applications
	+ Established ten person organising committee
* Accommodation
	+ Researched and reached out to more than a dozen accommodation providers
	+ Inspected six accommodation options and received quotes from five
	+ In consultation with my team, the President and VP (finance) three accommodation contracts were drawn up, reviewed and signed off
* Venues
	+ High Court of Australia confirmed as venue for mooting grand final with a high court justice to preside
	+ Discussions are progressing positively with ANU
	+ In discussion with Australian Parliament House to host closing gala in the Marble Foyer and Great Hall
* Publicity
	+ Comprehensive publicity plan developed
* Sponsorship
	+ Sponsorship and partnership ideas brainstormed and sponsorship plan developed
	+ Sponsorship director resigned June 2016
* Finances
	+ Draft budget drawn up
	+ Rough ticket prices locked in

# What happens before September council

* Complete financial handover following 2016 Conference
* Finalise venue and room bookings
* Recruit new sponsorship director and begin pursuing sponsorship goals in coordination with ALSA Sponsorship Officer
* Begin implementing publicity plan